## Sheet1
Sprint 3 Backlog
Hours Remaining on Day
Importance | Task | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday
1 | Client GUI | 5 | 5 | 5 | 0 | 0 | 0 | 0
2 | Enable Mouse Interaction | 3 | 3 | 3 | 0 | 0 | 0 | 0
3 | Enable Difficulty Selection | 1 | 1 | 1 | 1 | 1 | 0 | 0
4 | Allow for New Games | 1 | 1 | 1 | 1 | 1 | 0 | 0
5 | Fix NegaMax AI and Heuristic Functions | 3 | 3 | 3 | 3 | 3 | 3 | 0